## Sheet1
GANTT CHART - PROJECT TIMELINE
Activity | March | April | [29 empty] | May
| 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Pre Meeting
Create MoM
Create Pre Meeting Notes
Create Business Process Document
Create Use Case Diagram for As Is Process
Create Activity Diagram for As Is Process
Create Use Case Diagram for To Be Process
Create Activity Diagram for To Be Process
Create Gantt Chart
Create ERD
Create Data Flow Diagram Level 0
Create Data Flow Diagram Level 1
Create Data Flow Diagram Level 2
Create UI/UX
Testing on Sign Up Feature
Testing on Login Feature
Testing on Product Search & Filtering Feature
Testing on Shopping Cart & Checkout Feature
Testing on Payment system Feature
Testing on Order Track Feature
Testing on Rating & Review Feature